## Avalanche - Deliverable 1
Title | URL | Assignees | Status | Priority🔥 | Task Type📁 | Iteration🔄 | Repository | Story Points❤️‍🔥
Write a system request, feasibility analysis, cost benefit analysis and a project methodology. |  | Aman440501, chiaigwe, DhulfiqarH, hsayini7078, nissubba1, tnisbett1995 | Todo🗂️ | High💀 | Research | Iteration🔄 1 |  | Point 5
Identify and collect data about different payroll systems and how we can apply it to the project. |  | Aman440501, chiaigwe | Todo🗂️ | Medium😬 | Research | Iteration🔄 1 |  | Point 3
Find the different software tools that would be using to write codes. |  | DhulfiqarH, hsayini7078 | Todo🗂️ | Low🥶 | Research | Iteration🔄 1 |  | Point 3
Gather research as to which database software tool is best to use. |  | nissubba1 | Todo🗂️ | Low🥶 | Research | Iteration🔄 1 |  | Point 4
Division of Work/Roles | https://github.com/tnisbett1995/IS-436-Group-7-Project/issues/10 |  | Done✅ | High💀 | Team Assignment | Iteration🔄 1 | tnisbett1995/IS-436-Group-7-Project | Point 1
Deliverable 1 System request | https://github.com/tnisbett1995/IS-436-Group-7-Project/issues/1 |  | Done✅ | High💀 | Deliverable | Iteration🔄 1 | tnisbett1995/IS-436-Group-7-Project | Point 1
GitHub Project Customization | https://github.com/tnisbett1995/IS-436-Group-7-Project/issues/6 |  | Done✅ | High💀 | Design🛠️ | Iteration🔄 1 | tnisbett1995/IS-436-Group-7-Project | Point 3
Set-Up GitHub Collaboration | https://github.com/tnisbett1995/IS-436-Group-7-Project/issues/7 |  | Done✅ | High💀 | Team Assignment | Iteration🔄 1 | tnisbett1995/IS-436-Group-7-Project | Point 1
Discuss Project Proposal | https://github.com/tnisbett1995/IS-436-Group-7-Project/issues/8 |  | Done✅ | High💀 | Team Assignment | Iteration🔄 1 | tnisbett1995/IS-436-Group-7-Project | Point 2
Implement Feedback from D1 | https://github.com/tnisbett1995/IS-436-Group-7-Project/issues/9 |  | Done✅ | Medium😬 | Feedback | Iteration🔄 2 | tnisbett1995/IS-436-Group-7-Project | Point 1
Work on list of use cases |  |  | Todo🗂️ | Medium😬 | User Accessibility | Iteration🔄 2 |  | Point 3
Choose 5 Use cases and work on documentation + Diagram |  |  | Todo🗂️ | High💀 | User Accessibility | Iteration🔄 2 |  | Point 4
Use case analysis |  |  | Todo🗂️ | Medium😬 | User Accessibility | Iteration🔄 2 |  | Point 4
Finish and Submit Deliverable 2 |  |  | Todo🗂️ | High💀 | Feedback | Iteration🔄 2 |  | Point 4
ERD Diagram and documentation |  |  | Backlog🗃️ | Low🥶 | Documentation📄 | Iteration🔄 3 |  | Point 3
Website Design |  |  | Backlog🗃️ | Medium😬 | Design🛠️ | Iteration🔄 3 |  | Point 5
Make UI/UX Design |  |  | Backlog🗃️ | Low🥶 | Design🛠️ | Iteration🔄 3 |  | Point 4
Choose Database and start working on it |  |  | Backlog🗃️ | Low🥶 | Database | Iteration🔄 3 |  | Point 3
Implement Feedback from Deliverable 2 |  |  | Backlog🗃️ | High💀 | Feedback | Iteration🔄 3 |  | Point 1
Start writing initial code -HTML/CSS |  |  | Backlog🗃️ | Low🥶 | Frontend | Iteration🔄 3 |  | Point 4
Start working on JavaScript and PHP |  |  | Backlog🗃️ | Low🥶 | Backend | Iteration🔄 3 |  | Point 5
Start making website Responsive |  |  | Backlog🗃️ | Low🥶 | Frontend | Iteration🔄 3 |  | Point 5
Integration of Code |  |  | Backlog🗃️ | Low🥶 | Team Coding💻 | Iteration🔄 3 |  | Point 5
Choose Framework |  |  | Backlog🗃️ | Low🥶 | Research | Iteration🔄 3 |  | Point 2
Work on Functionality and user quality assurance |  |  | Backlog🗃️ | Low🥶 | User Accessibility | Iteration🔄 3 |  | Point 3
Start doing Backend Development and Database |  |  | Backlog🗃️ | Low🥶 | Backend | Iteration🔄 3 |  | Point 5
Test the code and User Quality Assurance |  |  | Backlog🗃️ | Low🥶 | User Accessibility | Iteration🔄 3 |  | Point 2
Implement Feedback from D3 |  |  | Backlog🗃️ | Low🥶 | Feedback | Iteration🔄 3 |  | Point 1
Bug fixes and Debugging |  |  | Backlog🗃️ | Low🥶 | Team Coding💻 | Iteration🔄 3 |  | Point 4
Finish Backend Dvelopment |  |  | Backlog🗃️ | Low🥶 | Backend | Iteration🔄 3 |  | Point 4
Final Quality Assurance Check |  |  | Backlog🗃️ | Low🥶 | User Accessibility | Iteration🔄 3 |  | Point 3
Implement Feedback from D4 |  |  | Backlog🗃️ | Low🥶 | Feedback | Iteration🔄 3 |  | Point 1
Project Presentation DEMO |  |  | Backlog🗃️ | Low🥶 | Team Assignment | Iteration🔄 4 |  | Point 1
Submit Final Code and App |  |  | Backlog🗃️ | Low🥶 | Deliverable | Iteration🔄 4 |  | Point 5
Finalize All Documentation |  |  | Backlog🗃️ | Low🥶 | Documentation📄 | Iteration🔄 4 |  | Point 5
Come up with questionnaire and Conduct Interview. Record observation and Research - Regular Employee Position |  | hsayini7078 | In Progress🏗️ | High💀 | Research | Iteration🔄 2 |  | Point 4
Come up with questionnaire and Conduct Interview. Record observation and Research - Manager Position |  | nissubba1 | In Progress🏗️ | High💀 | Research | Iteration🔄 2 |  | Point 4
Case Analysis, case documents and use case diagrams. |  | Aman440501, DhulfiqarH | In Progress🏗️ | High💀 | User Accessibility | Iteration🔄 2 |  | Point 4
Functional and non functional requirements |  | tnisbett1995 | In Progress🏗️ | High💀 | User Accessibility | Iteration🔄 2 |  | Point 3